## Slide 1
PRODUCT ROADMAP
ThePetsVault
From trusted pet profiles to a live Karachi pilot
AI-Powered Pet Care & Marketplace Ecosystem
Stakeholder presentation | FAST-NUCES Karachi | Fall 2026

## Slide 2
The Product in One Page
Four everyday pet needs, one trusted platform, one pet profile
Buy & Sell Pets
Verified sellers, protected payments, reporting
Pet Sitting
Find a trusted sitter and book while you travel
Vet Care
Licensed vets, appointments and video consults
Food & Accessories
Catalog from verified vendors, delivered to you
UNIFIED PET PROFILE - identity | vaccination & health records | bookings | purchases
AI: personalised discovery | support chatbot | vet triage
TRUST: verified users | ratings | safe payments | audit trail
4
service pillars
11
epics
29
user stories
PKR 4.8M
budget (BAC)
12
months
ThePetsVault | Product Roadmap
2

## Slide 3
THE ROAD TO LAUNCH
PRODUCT ROADMAP: SIX STOPS FROM FOUNDATION TO GO-LIVE
FOUNDATION
1
M1-M3 Validated plan & design
Requirements baseline, UX prototype, architecture, cloud & CI/CD base
TRUST
2
M3-M5 Verified users & pet profiles
Sign-up, roles & KYC; pet profile, vaccination records, document access
MARKETPLACE
3
M4-M6 Safe pet buying & selling
Listings & search, messaging, protected payment, refunds, disputes & audit
CARE
4
M5-M7 Sitting & vet care
Sitter booking & ratings; vet licence, slots, video consults; reminders
SHOP & SMART
5
M6-M8 Store, AI & admin
Food store, personalised discovery, support chatbot, vet triage, admin dashboard
LAUNCH
6
M9-M12 Test, pilot & go-live
UAT & security tests, Karachi pilot, hardening, privacy controls, deployment
P-I GATE: M6
Stops overlap. Months are project months (M1 = start of Fall 2026). Practicum-I covers M1-M6, Practicum-II covers M7-M12.

## Slide 4
What Each Stop Delivers
All 29 user stories placed on the road
1 FOUNDATION (M1-M3)
Business validation & personas
Requirements & scope baseline
UX prototype for all roles
Architecture, data model, API contract
Cloud environments & CI/CD
2 TRUST (M3-M5)
User Registration & Login
Role-Based Access Control
KYC / Identity Verification
Pet Profile Creation & Management
Vaccination & Medical History
Document Upload & Access Permissions
3 MARKETPLACE (M4-M6)
Listing Creation & Management
Marketplace Search & Discovery
Buyer-Seller Messaging & Transaction Flow
Listing Moderation & Reporting
Platform-Mediated Payment Processing
Cancellation, Refunds & Disputes
Audit Trail & Admin Moderation Queue
4 CARE (M5-M7)
Sitter Profile & Availability
Sitting Booking, Instructions & Cancellation
Sitting Check-In Updates & Ratings
Vet Availability & Professional Verification
Vet Discovery & Appointment Scheduling
Tele-Consultation & Consultation Records
Vet Ratings & Reviews
Notifications & Reminders
5 SHOP & SMART (M6-M8)
Product Catalog & Vendor Management
Cart, Checkout & Product Recommendations
Order Tracking & Product Reviews
Personalized Pet Discovery (AI)
Grounded Support Chatbot (AI)
Veterinary Triage & Red-Flag Routing (AI)
Admin Dashboard & Secure Access
6 LAUNCH (M9-M12)
Account Deletion & Data Privacy
UAT with users, vet expert & partners
Security, performance & integration testing
Karachi pilot across all 4 pillars
Pilot fixes, runbooks & partner training
Production deployment & closure
ThePetsVault | Product Roadmap
4

## Slide 5
Beyond the First Release
What comes after the MVP, and what stays out of scope
Next (if time allows)
Pet-specific product recommendations
Sitter check-in photo updates
Saved searches & recurring product reminders
Automated vaccination & appointment reminders
Promoted / featured listings
Later (future horizon)
Subscription / Plus membership
Advanced collaborative recommendations
Pet microchip integration
Adoption / NGO social-impact module
Insurance partner integration
Not in the MVP
AI medical diagnosis or predictive health analytics
Owned warehouses, boarding facilities or delivery fleet
Custom payment rail or regulated escrow custody
Nationwide launch before the Karachi pilot
Protected wildlife or illegal animal trading
ThePetsVault | Product Roadmap
7